## Overview
Items | Count
Total Features: | 48
Functional features: | 39
Total User Stories: | 397
Covered User Stories
Test Cases Count:

## Sheet1
Due dates | (Multiple Items)
Row Labels | Sum of Estimated Effort
Gurudas | 19
harsha | 10
Kishore | 47.5
Laxmi | 27
Nath Harsha | 46.5
Susmitha | 32.5
Grand Total | 182.5

## Release 2a Features
Project: Global IT Server: bdo.visualstudio.com\bdo Query: [None] List type: Flat
ID | Work Item Type | Title | Assigned To | State | Value Area | Type | Estimated Effort | Due dates
11706 | Feature | Rules for document manager | Nath Harsha | New | Business | Simple | 4 | 2017-09-11
11411 | User Story | View current library FSAs | Holger | Closed | Business
18968 | User Story | Add new FSA to the library | Holger | Closed | Business
18996 | User Story | Filter FSA maintain screen | Nagaraj Puttakota (RAJ) | Closed | Business
18997 | User Story | Update an FSA in the library | Holger | Closed | Business
18998 | User Story | Delete a FSA from the library | Holger | Closed | Business
20934 | User Story | Add all available industry tags as default into the scope | Holger | Closed | Business
21666 | User Story | Update the sort order FSAs in the library | Holger | Closed | Business
25613 | User Story | Update an FSA in the library - properties screen | Viswanathan Vidyanathapuran | Closed | Business
33046 | User Story | Classification option should have 3 more options | Nagaraj Puttakota (RAJ) | Closed | Business
36619 | User Story | Correct the icons/images in the FSA screens for Library | Viswanathan Vidyanathapuran | Closed | Business
56963 | User Story | Fix scoping formula | Nagaraj Puttakota (RAJ) | Closed | Business
63414 | User Story | Introducing details panel in FSA screen | Shraddha Khare | Closed | Business
14870 | Feature | Data Model Implementation |  | Active | Architectural
14871 | User Story | Validate that all High Level US can be realized with the data model | Sree Adigopula | Closed | Architectural
15503 | User Story | Implement the designed data model in Entity Framework Core 1.0 - Code-First | Henk Van De Crommert | Closed | Architectural
74284 | User Story | Team 3 - Upgrade the current data model for the current insights for preview, review & publish process | Sree Adigopula | Closed | Architectural
85297 | User Story | Team 5 - Upgrade the current data model for the current insights for preview, review & publish process | Sree Adigopula | Closed | Architectural
85298 | User Story | Team 7 - Upgrade the current data model for the current insights for preview, review & publish process | Sree Adigopula | Closed | Architectural
11403 | Feature | Maintain Financial Statement Areas (FSA) - International | Nath Harsha | Active | Business | Complex | 10 | 2017-09-12
109470 | User Story | Fix scoping formula - GetDuplicateCodes | Ivan Ashish Paul | Active | Business
109472 | User Story | Fix scoping formula - GetDuplicateIds | Ivan Ashish Paul | Active | Business
109482 | User Story | Fix scoping formula - GetDocumentDuplicateIndexNumbers | Ivan Ashish Paul | Active | Business
116170 | User Story | Validate leadsheet codes - Duplicate code | Pooja Garg | Active | Business
10032 | User Story | Validate library - Duplicate index numbers | Nagaraj Puttakota (RAJ) | Closed | Business
25486 | User Story | View validation | Nagaraj Puttakota (RAJ) | Closed | Business
25487 | User Story | Validate workspace settings - Verify scope | Nagaraj Puttakota (RAJ) | Closed | Business
25577 | User Story | Validate document manager - inconsistent index numbers | Nagaraj Puttakota (RAJ) | Closed | Business
25609 | User Story | Validate GATs - Duplicate ID | Nagaraj Puttakota (RAJ) | Closed | Business
25610 | User Story | Validate risks - Duplicate ID | Nagaraj Puttakota (RAJ) | Closed | Business
25611 | User Story | Validate cycles - Duplicate code | Nagaraj Puttakota (RAJ) | Closed | Business
25612 | User Story | Validate FSA audit tests - Duplicate ID | Nagaraj Puttakota (RAJ) | Closed | Business
25619 | User Story | Validate FSA/risks links | Nagaraj Puttakota (RAJ) | Closed | Business
25620 | User Story | Validate FSA/audit tests links | Nagaraj Puttakota (RAJ) | Closed | Business
25621 | User Story | Validate FSA/cycles links | Nagaraj Puttakota (RAJ) | Closed | Business
55255 | User Story | Filter validation screen | Stephan Matthee | Closed | Business
56661 | User Story | Technical design Library Validation | Stefan Hamels - BDO-NL | Closed | Architectural
58328 | User Story | Validate library - max file size | Stephan Matthee | Closed | Business
65653 | User Story | [Library] Library validation mechanism | Sree Adigopula | Closed | Architectural
66084 | User Story | [Library] Create a LibraryValidationQueue | Sree Adigopula | Closed | Architectural
77176 | User Story | Validate FSA/review audit tests links | Nagaraj Puttakota (RAJ) | Closed | Business
77177 | User Story | Validate review audit tests - Duplicate ID | Nagaraj Puttakota (RAJ) | Closed | Business
79753 | User Story | Validate documents - invalid file type | Nagaraj Puttakota (RAJ) | Closed | Business
85171 | User Story | Validate warning - Duplicate ID | Nagaraj Puttakota (RAJ) | Closed | Business
100844 | User Story | Validate that workspace settings do not exists in duplicate scope | Shraddha Khare | Closed | Business
108946 | User Story | Validate Risk - Risk is marked as InUse but linked FSA is not | Shraddha Khare | Closed | Business
108947 | User Story | Validate Test - Test is marked as InUse but the linked FSA is not | Shraddha Khare | Closed | Business
116177 | User Story | Validate Materiality - mandatory fields | Shraddha Khare | Ready | Business
25490 | User Story | Validate audit tests - Orphaned links to FSAs | Shraddha Khare | Resolved | Business
25491 | User Story | Validate FSAs - Orphaned links to Cycles | Shraddha Khare | Resolved | Business
25492 | User Story | Validate GAT - Orphaned links to GAA | Shraddha Khare | Resolved | Business
25494 | User Story | Validate FSAs - Duplicate code | Nagaraj Puttakota (RAJ) | Resolved | Business
25608 | User Story | Validate GAAs - Duplicate code | Nagaraj Puttakota (RAJ) | Resolved | Business
90458 | User Story | Validate Risks - Orphaned links to FSAs | Shraddha Khare | Resolved | Business
90459 | User Story | Validate Review Audit Test - Orphaned links to FSAs | Shraddha Khare | Resolved | Business
25770 | Feature | Technical design for Engagement Reporting |  | Active | Architectural
26848 | User Story | Risk Report | Ankita Nandy | Active | Business
25345 | User Story | Technical design for Client-side reporting | Stefan Hamels - BDO-NL | Closed | Architectural
54650 | User Story | [Reporting] Reportviewer for loading reports | Sree Adigopula | Closed | Architectural
63897 | User Story | [Reporting] Create an infrastructural reporting project | Sree Adigopula | Closed | Architectural
63908 | User Story | [Reporting] Create an OData application for reporting | Sree Adigopula | Ready | Architectural
14751 | Feature | Rules for warnings | Kishore | New | Business | Simple | 4 | 2017-09-12
92286 | User Story | Maintain the available entities for each engagement type | Shraddha Khare | Closed | Business
9835 | Feature | Maintain WorkspaceSettings | Kishore | New | Business | Medium | 7.5 | 2017-09-13
10023 | User Story | Create and update changeset for current library changes | Nagaraj Puttakota (RAJ) | Closed | Business
10024 | User Story | View current changeset/ Summary of changes | Nagaraj Puttakota (RAJ) | Closed | Business
10031 | User Story | View previous changesets/ Summary of changes |  | Closed | Business
25574 | User Story | Technical design for the different environments required | Stefan Hamels - BDO-NL | Closed | Architectural
67648 | User Story | Database design for library | Alexey Evlampiev | Closed | Architectural
96185 | User Story | Different library base can be selected from the base selection | Shraddha Khare | Closed | Business
10039 | User Story | Publish library changeset | Shraddha Khare | Resolved | Business
11408 | Feature | Maintain Materiality | Laxmi | New | Business | Medium | 7.5 | 2017-09-13
9696 | User Story | UX Document manager maintain screen | Ben Smeets | Closed | Business
11216 | User Story | Add document to the library via drag and drop | Nagaraj Puttakota (RAJ) | Closed | Business
11217 | User Story | Update scope of a document in the library | Nagaraj Puttakota (RAJ) | Closed | Business
11219 | User Story | Remove a document from the library | Nagaraj Puttakota (RAJ) | Closed | Business
11221 | User Story | Update document in the library | Nagaraj Puttakota (RAJ) | Closed | Business
11222 | User Story | Move document to another folder in library | Nagaraj Puttakota (RAJ) | Closed | Business
11259 | User Story | Add a new folder to the library | Nagaraj Puttakota (RAJ) | Closed | Business
11260 | User Story | View document/folder properties in the library | Nagaraj Puttakota (RAJ) | Closed | Business
12339 | User Story | Mandatory Checkbox on Property Screen |  | Closed | Business
17222 | User Story | Move a folder with its entire nested content - drag & drop | Nagaraj Puttakota (RAJ) | Closed | Business
20102 | User Story | Show document manager as defined in library by default | Michael Lettroy | Closed | Business
20882 | User Story | Remove a folder from the library | Nagaraj Puttakota (RAJ) | Closed | Business
21242 | User Story | Add a new placeholder/manual document object to the library | Nagaraj Puttakota (RAJ) | Closed | Business
21246 | User Story | Delete a placeholder/ manual document from the library | Nagaraj Puttakota (RAJ) | Closed | Business
21251 | User Story | Update placeholder/ manual document objects | Nagaraj Puttakota (RAJ) | Closed | Business
21267 | User Story | View current document manager as defined by the library | Nagaraj Puttakota (RAJ) | Closed | Business
21330 | User Story | Update folder in the library | Nagaraj Puttakota (RAJ) | Closed | Business
21925 | User Story | Add a new report document to the library | Nagaraj Puttakota (RAJ) | Closed | Business
21926 | User Story | Add a new questionnaire to the library | Nagaraj Puttakota (RAJ) | Closed | Business
21928 | User Story | Update properties for questionnaires in the library | Nagaraj Puttakota (RAJ) | Closed | Business
21929 | User Story | Update properties for reports in the library | Nagaraj Puttakota (RAJ) | Closed | Business
21931 | User Story | Delete a questionnaire from the library | Nagaraj Puttakota (RAJ) | Closed | Business
23781 | User Story | Save last searched scope previous scope filter in browser cookie | Stephan Matthee | Closed | Business
25564 | User Story | Update the order of document items in the library | Nagaraj Puttakota (RAJ) | Closed | Business
32149 | User Story | Document Template Management - GET | Sree Adigopula | Closed | Architectural
35982 | User Story | View questionnaire properties in the library | Nagaraj Puttakota (RAJ) | Closed | Business
55111 | User Story | Document Template Management - ADD | Sree Adigopula | Closed | Architectural
56065 | User Story | View placeholders/manual document object properties in the library | Nagaraj Puttakota (RAJ) | Closed | Business
56927 | User Story | PoC for document and structure screens | Holger | Closed | Business
58100 | User Story | Max depth for document structure in library | Nagaraj Puttakota (RAJ) | Closed | Business
58119 | User Story | Max file size and forbidden filetypes for documents uploaded to the library | Stephan Matthee | Closed | Business
59015 | User Story | All IsInUse properties should be selected by default when a new library items is added | Nagaraj Puttakota (RAJ) | Closed | Business
66458 | User Story | Add document to the library via ... menu | Nagaraj Puttakota (RAJ) | Closed | Business
69673 | User Story | Index numbers can contain alphanumeric characters | Nagaraj Puttakota (RAJ) | Closed | Business
71676 | User Story | Sign-off before archive property for document, placeholder, questionnaire and reports | Nagaraj Puttakota (RAJ) | Closed | Business
98247 | User Story | Maintain SignOffNotRequired property in the library | Shraddha Khare | Closed | Business
84419 | User Story | API Implementation of Sign-off before archive property for document, placeholder, questionnaire and reports | Nagaraj Puttakota (RAJ) | Resolved | Business
11404 | Feature | Maintain General Audit Areas (GAA) - International | Nath Harsha | New | Business | Medium | 7.5 | 2017-09-14
85263 | User Story | Maintain Initial Scoping Questionnaire Big8 - International | Kishore Penugonda | Active | Business
85264 | User Story | Preview changes made to the Big8 | Yasin Mahammad | Active | Business
85271 | User Story | Remove a change made to the Big8 from the preview list | Yasin Mahammad | Active | Business
85295 | User Story | Only allow scoping tags that are allowed in Initial Scoping maintain screen | Pooja Garg | Active | Business
92197 | User Story | Publish changes made to the Big8 | Rahul Sawhney | Active | Business
11766 | Feature | Rules for audit tests | Kishore | New | Business | Simple | 4 | 2017-09-14
10043 | User Story | Update library settings | Nagaraj Puttakota (RAJ) | Closed | Business
11410 | User Story | View current library settings | Nagaraj Puttakota (RAJ) | Closed | Business
20702 | User Story | Edit Scoped in assertions for automatically scoped in FSAs | Monish C Mohan | Closed | Business
21662 | User Story | Add new library settings | Nagaraj Puttakota (RAJ) | Closed | Business
21679 | User Story | Sign off planning as EP | Michael Lettroy | Closed | Business
21743 | User Story | Delete a workspace setting from the library | Nagaraj Puttakota (RAJ) | Closed | Business
21959 | User Story | Edit Scoped in assertions for manually scoped in FSAs | Viswanathan Vidyanathapuran | Closed | Business
22857 | User Story | Preview changes for workspace settings screen before publishing | Nagaraj Puttakota (RAJ) | Closed | Business
25935 | User Story | Filter workspace settings in maintain settings screen | Nagaraj Puttakota (RAJ) | Closed | Business
63422 | User Story | Introducing details panel in settings screen | Shraddha Khare | Closed | Business
69787 | User Story | Drop-down showing all available workspace settings should be in alphabetical order | Stephan Matthee | Closed | Business
91244 | User Story | Filter on Workspace setting ID column should be free text rather than drop-down | Shraddha Khare | Closed | Business
73640 | User Story | Publish Workspace Settings changes to next environment | Shraddha Khare | Resolved | Business
22804 | Feature | Maintain Cycles - Publish international library | Laxmi | New | Business | Simple | 4 | 2017-09-14
11412 | User Story | View current library GAAs | Viswanathan Vidyanathapuran | Closed | Business
19009 | User Story | Add new GAA to the library | Viswanathan Vidyanathapuran | Closed | Business
19010 | User Story | Update a GAA in the library | Viswanathan Vidyanathapuran | Closed | Business
19011 | User Story | Delete a GAA from the library | Viswanathan Vidyanathapuran | Closed | Business
25561 | User Story | Update sort order of GAAs in the library | Viswanathan Vidyanathapuran | Closed | Business
25929 | User Story | Filter GAA maintain screen | Nagaraj Puttakota (RAJ) | Closed | Business
63416 | User Story | Introducing details panel in GAA screen | Shraddha Khare | Closed | Business
57986 | Feature | Other rules | Gurudas | New | Business | Simple | 4 | 2017-09-14
61342 | User Story | Review navigation options for details window | Pushpdeep Gupta | Active | Business
11413 | User Story | View current library FSA tests | Omkarachary K | Closed | Business
19045 | User Story | Filter review audit test maintain screen | Stephan Matthee | Closed | Business
19046 | User Story | Add new FSA audit test to the library | Omkarachary K | Closed | Business
19047 | User Story | Update a FSA audit test in the library | Omkarachary K | Closed | Business
19048 | User Story | Delete a FSA audit test from the library | Nagaraj Puttakota (RAJ) | Closed | Business
25546 | User Story | View current library GAA tests | Viswanathan Vidyanathapuran | Closed | Business
25547 | User Story | Add new GAA audit test to the library | Viswanathan Vidyanathapuran | Closed | Business
25548 | User Story | Update a GAA audit test in the library | Viswanathan Vidyanathapuran | Closed | Business
25549 | User Story | Delete a GAA audit test from the library | Viswanathan Vidyanathapuran | Closed | Business
25550 | User Story | Update sort order of FSA audit tests | Omkarachary K | Closed | Business
25551 | User Story | Update sort order of GAA audit tests | Viswanathan Vidyanathapuran | Closed | Business
25898 | User Story | Add new Review Engagement test to the library | MLettroy | Closed | Business
25899 | User Story | Delete a review test from the library | Nagaraj Puttakota (RAJ) | Closed | Business
25900 | User Story | Update a review test in the library | Nagaraj Puttakota (RAJ) | Closed | Business
25901 | User Story | Update sort order of review tests(reordering) | Stephan Matthee | Closed | Business
25902 | User Story | View current library review tests | Stephan Matthee | Closed | Business
25933 | User Story | Filter FSA audit test maintain screen | Holger | Closed | Business
27358 | User Story | Delete FSA from FSA audit test assertions list (FSA audit tests) | Nagaraj Puttakota (RAJ) | Closed | Business
55260 | User Story | Filter GAA audit tests in maintain screen | Nagaraj Puttakota (RAJ) | Closed | Business
64128 | User Story | New FSA audit test type - Data Analytics (DAT) | Nagaraj Puttakota (RAJ) | Closed | Business
105382 | User Story | Audit tests and risks cannot be linked to the same FSA twice | Shraddha Khare | Closed | Business
11406 | Feature | Maintain Risks - International | Nath Harsha | New | Business | Medium | 7.5 | 2017-09-15
11414 | User Story | View current library risks | Nagaraj Puttakota (RAJ) | Closed | Business
19056 | User Story | Filter risk maintain screen | Nagaraj Puttakota (RAJ) | Closed | Business
19057 | User Story | Add new risk to the library | Nagaraj Puttakota (RAJ) | Closed | Business
19058 | User Story | Update a risk in the library | Nagaraj Puttakota (RAJ) | Closed | Business
19059 | User Story | Delete a risk from the library | Nagaraj Puttakota (RAJ) | Closed | Business
25565 | User Story | Update sort order of risks in the library | Nagaraj Puttakota (RAJ) | Closed | Business
91245 | User Story | Add Title column to Risk list | Shraddha Khare | Closed | Business
14736 | Feature | Rules for risks | Kishore | New | Business | Simple | 4 | 2017-09-15
11415 | User Story | View current library cycles | Viswanathan Vidyanathapuran | Closed | Business
19066 | User Story | Add new cycle to the library | Viswanathan Vidyanathapuran | Closed | Business
19067 | User Story | Update a cycle in the library | Viswanathan Vidyanathapuran | Closed | Business
19068 | User Story | Delete a cycle from the library | Viswanathan Vidyanathapuran | Closed | Business
21871 | User Story | Add cycle from library | Michael Lettroy | Closed | Business
25926 | User Story | Filter cycle maintain screen | Nagaraj Puttakota (RAJ) | Closed | Business
25936 | User Story | Update sort order of cycles | Viswanathan Vidyanathapuran | Closed | Business
59557 | User Story | ID field for cycles to be added | Nagaraj Puttakota (RAJ) | Closed | Business
63415 | User Story | Introducing details panel in cycle screen | Shraddha Khare | Closed | Business
14880 | Feature | Library API Services | Kishore | New | Architectural | Complex | 10 | 2017-09-15
11416 | User Story | View current library materiality | Nagaraj Puttakota (RAJ) | Closed | Business
22847 | User Story | Preview changes for materiality maintain screen before publishing | Nagaraj Puttakota (RAJ) | Closed | Business
22850 | User Story | Update the materiality benchmarks that are already included in the library | Nagaraj Puttakota (RAJ) | Closed | Business
23113 | User Story | Add a new materiality benchmark value to the library | Nagaraj Puttakota (RAJ) | Closed | Business
23114 | User Story | Delete a materiality benchmark value from the library | Nagaraj Puttakota (RAJ) | Closed | Business
23416 | User Story | Update Clearly trivial values | Nagaraj Puttakota (RAJ) | Closed | Business
23417 | User Story | Update performance materiality % range in the library | Nagaraj Puttakota (RAJ) | Closed | Business
25930 | User Story | Filter materiality benchmarks | Nagaraj Puttakota (RAJ) | Closed | Business
63418 | User Story | Introducing details panel in materiality screen | Shraddha Khare | Closed | Business
22848 | User Story | Publish Materiality settings changes to next environment | Shraddha Khare | Resolved | Business
22825 | Feature | Maintain General Audit Areas (GAA) - Publish international library | Laxmi | New | Business | Simple | 4 | 2017-09-15
11758 | User Story | Business logic - Enable a document | Nagaraj Puttakota (RAJ) | Closed | Business
11760 | User Story | Business logic - Disable a document | Nagaraj Puttakota (RAJ) | Closed | Business
11764 | User Story | Business logic - Enable a folder | Nagaraj Puttakota (RAJ) | Closed | Business
11765 | User Story | Business logic - Disable a folder | Nagaraj Puttakota (RAJ) | Closed | Business
25916 | User Story | Business logic - Disable a placeholder | Nagaraj Puttakota (RAJ) | Closed | Business
25917 | User Story | Business logic - Enable a placeholder | Nagaraj Puttakota (RAJ) | Closed | Business
35983 | Feature | Questionnaire - Question types | Susmitha | New | Business | Complex | 10 | 2017-09-15
11586 | User Story | Delete a rule - UX | Nagaraj Puttakota (RAJ) | Closed | Business
11715 | User Story | Add a new rule - UX | Nagaraj Puttakota (RAJ) | Closed | Business
36569 | User Story | Edit an existing rule - UX | Nagaraj Puttakota (RAJ) | Closed | Business
104827 | User Story | Rules outline - Show all rules per questionnaire (Simple) | sasathar | Ready | Business
25485 | Feature | Validate library | Nath Harsha | Active | Business | Complex | 10 | 2017-09-18
14713 | User Story | Business Logic - Enable an audit test | Nagaraj Puttakota (RAJ) | Closed | Business
14714 | User Story | Business Logic - Disable an audit test | Nagaraj Puttakota (RAJ) | Closed | Business
25912 | User Story | Business Logic - Disable an GAA test | Nagaraj Puttakota (RAJ) | Closed | Business
25913 | User Story | Business Logic - Enable an GAA test | Nagaraj Puttakota (RAJ) | Closed | Business
25914 | User Story | Business Logic - Disable an review test | Nagaraj Puttakota (RAJ) | Closed | Business
25915 | User Story | Business Logic - Enable an review audit test | Nagaraj Puttakota (RAJ) | Closed | Business
11886 | Feature | Localization |  | New | Architectural
14845 | User Story | Due Diligence on Localization | Sree Adigopula | Closed | Architectural
14846 | User Story | Remediation on Localization | Sree Adigopula | Closed | Architectural
19799 | User Story | Technical design for Application Localization and Globalization | Henk Van De Crommert | Ready | Architectural
12041 | Feature | UX Standardization |  | New | Architectural
13954 | User Story | Standard UX: Visual UI Interaction Components / Styleguide | Carolina García León | Closed | Architectural
13956 | User Story | Standard UX: Grid Component | Carolina García León | Closed | Architectural
13957 | User Story | Standard UX: Panel Behavior | Carolina García León | Closed | Architectural
13958 | User Story | Standard UX: Time-scape | Carolina García León | Closed | Architectural
68248 | User Story | Standard UX: References | Carolina García León | Closed | Architectural
68250 | User Story | Standard UX: Fluid | Carolina García León | Closed | Architectural
68246 | User Story | Standard UX: Keyboard Navigation | Carolina García León | Ready | Architectural
68249 | User Story | Standard UX: Wording | Carolina García León | Ready | Architectural
12043 | Feature | Application server configuration settings |  | New | Architectural
17553 | User Story | Ensure that all client-server communication over SSL channel | Sree Adigopula | Closed | Architectural
17554 | User Story | Ensure that all server-server communication is encrypted | Sree Adigopula | Closed | Architectural
13176 | Feature | Technical Designs for Library |  | New | Architectural
13177 | User Story | Library - Data Element Management | Henk Van De Crommert | Closed | Architectural
13178 | User Story | Technical design for Library - Questionnaire Management | Henk Van De Crommert | Closed | Architectural
13179 | User Story | Technical design for Library - Report Management | Stefan Hamels - BDO-NL | Closed | Architectural
14386 | User Story | Technical design for Library - Document Template Management | Ronny Verhallen - BDO-NL | Closed | Architectural
14392 | User Story | Technical design for Library - Configuration management | Ronny Verhallen - BDO-NL | Closed | Architectural
23888 | User Story | Technical design for Library - Authorization module | Ronny Verhallen - BDO-NL | Closed | Architectural
98080 | User Story | Technical design for Library - Questionnaire Management - APT client | Srinivasan Rakhunathan | Resolved | Architectural
14743 | Feature | Rules for FSA/GAA | Kishore | New | Business | Simple | 4 | 2017-09-18
53056 | User Story | View conditions/actions for rules | Nagaraj Puttakota (RAJ) | Closed | Business
53066 | User Story | Add a new clause based on field - single choice | Nagaraj Puttakota (RAJ) | Closed | Business
53067 | User Story | Add a new clause based on field - Number, Date | Nagaraj Puttakota (RAJ) | Closed | Business
53080 | User Story | Add a new clause based on field - multiple choice | Nagaraj Puttakota (RAJ) | Closed | Business
53506 | User Story | Delete a clause from a clause | Nagaraj Puttakota (RAJ) | Closed | Business
58173 | User Story | Add a new clause based on Initial Scoping Questions | Nagaraj Puttakota (RAJ) | Closed | Business
60970 | User Story | Preview and publish changes for rules in a questionnaire | Shraddha Khare | Closed | Business
85619 | User Story | Add a new clause based on field - drop down | Shraddha Khare | Closed | Business
86431 | User Story | Delete an action from a clause | Shraddha Khare | Closed | Business
22859 | Feature | Maintain Warnings - Publish international library | Laxmi | New | Business | Simple | 4 | 2017-09-18
36361 | User Story | Question field type - Drop-down based engagement data | Shraddha Khare | Closed | Business
54663 | User Story | View table properties in a questionnaire' | Shraddha Khare | Closed | Business
64851 | User Story | Update a field in a table - linked to points forward | Shraddha Khare | Closed | Business
71804 | User Story | Add a new column to a table | Shraddha Khare | Closed | Business
71805 | User Story | Update table properties | Shraddha Khare | Closed | Business
71806 | User Story | Update a column in a table | Shraddha Khare | Closed | Business
71807 | User Story | Delete a column in a table | Shraddha Khare | Closed | Business
71811 | User Story | Re-order a column in a table | Shraddha Khare | Closed | Business
71813 | User Story | Add a new row to a table | Shraddha Khare | Closed | Business
71814 | User Story | Delete a row in a table | Shraddha Khare | Closed | Business
71819 | User Story | Re-order a row in a table | Shraddha Khare | Closed | Business
72642 | User Story | Update a field in a table - linked to another table | Shraddha Khare | Closed | Business
72666 | User Story | Update a field in a table - linked to FSA | Shraddha Khare | Closed | Business
72667 | User Story | Update a field in a table - linked to cycles | Shraddha Khare | Closed | Business
72669 | User Story | Update a field in a table - linked to team explorer | Shraddha Khare | Closed | Business
79711 | User Story | Update a field in the table | Shraddha Khare | Closed | Business
79885 | User Story | Update a field in a table - linked to ETD points | Shraddha Khare | Closed | Business
79886 | User Story | Preview changes for manual/automatic tables in questionnaires before publishing | Shraddha Khare | Closed | Business
81719 | User Story | Update a field in the table - default value | Shraddha Khare | Closed | Business
79891 | User Story | Publish questionnaire table structure to next environment | Venkat Sai Gajendrula | Ready | Business
113070 | User Story | Preview changes for linked tables in questionnaires before publishing | Shraddha Khare | Resolved | Business
56155 | Feature | Validate questionnaires | Susmitha | New | Business | Medium | 7.5 | 2017-09-18
61189 | User Story | Part I - Preview a questionnaire in the library | Paanshul Dobriyal | Active | Business
83806 | User Story | Part II - Implement Scope Filtering for the questionnaire preview in the library | samisra | Active | Business
45849 | User Story | Provide the questionnaire properties | Nagaraj Puttakota (RAJ) | Closed | Business
63628 | User Story | Update questionnaire document properties | Shraddha Khare | Closed | Business
63928 | User Story | Expand/Collapse all sections and questions in a questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
81717 | User Story | Ensure that all changes being saved before leaving the screen - Questionnaires | Shraddha Khare | Closed | Business
93823 | User Story | Title field can be removed for text block | Shraddha Khare | Closed | Business
105527 | User Story | Ensure that all changes being saved before leaving the screen - Questionnaires - Part II | Ganapa Nagappa Kurni | Ready | Business
59229 | Feature | Maintain Tickmarks | Gurudas | New | Business | Medium | 7.5 | 2017-09-18
60855 | User Story | Render a section | Santhosh Raju V | Active | Business
36574 | User Story | Add a new section to a questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
36576 | User Story | Update an existing section in a questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
36577 | User Story | Delete a section in a questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
36578 | User Story | Move a section to an different position within the questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
54370 | User Story | Provide conditional formatting for a section | Nagaraj Puttakota (RAJ) | Closed | Business
61053 | User Story | Preview and publish changes made to a section in a questionnaire | Shraddha Khare | Closed | Business
61310 | User Story | Allow Section sign off | Shraddha Khare | Closed | Business
11407 | Feature | Maintain Cycles - International | Nath Harsha | New | Business | Medium | 7.5 | 2017-09-19
9848 | User Story | Add questions to a questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
9849 | User Story | Delete questions from a questionnaire | Stephan Matthee | Closed | Business
9866 | User Story | Provide conditional formatting for a question | Nagaraj Puttakota (RAJ) | Closed | Business
35980 | User Story | Update a question in a questionnaire | Stephan Matthee | Closed | Business
35984 | User Story | View current questionnaire setup | Nagaraj Puttakota (RAJ) | Closed | Business
59134 | User Story | Move a question to an different position within the questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
69670 | User Story | Questions in a questionnaire could have a title | Nagaraj Puttakota (RAJ) | Closed | Business
93808 | User Story | Character limits for questions in questionnaire to be increased | Shraddha Khare | Closed | Business
93822 | User Story | Improve behaviour on adding a new question | Shraddha Khare | Closed | Business
14744 | Feature | Rules for cycle | Kishore | New | Business | Simple | 4 | 2017-09-19
14738 | User Story | Business Logic - Enable a risk | Nagaraj Puttakota (RAJ) | Closed | Business
14739 | User Story | Business Logic - Disable a risk | Nagaraj Puttakota (RAJ) | Closed | Business
36580 | Feature | Questionnaires - Maintain Text block (help, instructions, warning) | Laxmi | New | Business | Medium | 7.5 | 2017-09-20
19021 | User Story | Business Logic - Enable a FSA | Nagaraj Puttakota (RAJ) | Closed | Business
19022 | User Story | Business Logic - Disable a FSA | Nagaraj Puttakota (RAJ) | Closed | Business
19023 | User Story | Business Logic - Enable a GAA | Nagaraj Puttakota (RAJ) | Closed | Business
19024 | User Story | Business Logic - Disable a GAA | Nagaraj Puttakota (RAJ) | Closed | Business
59346 | Feature | Maintain Leadsheet codes | Gurudas | New | Business | Medium | 7.5 | 2017-09-20
19025 | User Story | Business Logic - Enable a Cycle | Nagaraj Puttakota (RAJ) | Closed | Business
19026 | User Story | Business Logic - Disable a Cycle | Nagaraj Puttakota (RAJ) | Closed | Business
14728 | Feature | Questionnaire - Maintain Questions | Susmitha | New | Business | Medium | 7.5 | 2017-09-21
19027 | User Story | Business Logic - Enable a Warning | Nagaraj Puttakota (RAJ) | Closed | Business
19028 | User Story | Business Logic - Disable a Warning | Nagaraj Puttakota (RAJ) | Closed | Business
3352 | Feature | Publish libraries | Nath Harsha | New | Business | Complex | 10 | 2017-10-05
53068 | User Story | Library API: Get Questionnaire definition for a specific scope | srpotnur | Active | Architectural
115650 | User Story | [Library API] Enrich the Library API to provide more information to reduce the number of network calls | Neerudu Jeevan Reddy | Active | Architectural
117666 | User Story | [Library API] Update the 'big 8 scoping' service to include the defined dependencies | Appana Sandeep | Active | Architectural
35996 | User Story | Library API: Get Answer options for setting up a new engagement | Sree Adigopula | Closed | Architectural
35997 | User Story | Library API: Get library content for engagement scope | Sree Adigopula | Closed | Architectural
14726 | Feature | Questionnaire - Maintain Document | Laxmi | New | Business | Complex | 10 | 2017-10-10
18498 | User Story | View current library warnings | Nagaraj Puttakota (RAJ) | Closed | Business
19083 | User Story | Add new warning to the library | Nagaraj Puttakota (RAJ) | Closed | Business
19084 | User Story | Update a warning in the library | Nagaraj Puttakota (RAJ) | Closed | Business
19085 | User Story | Delete a warning from the library | Nagaraj Puttakota (RAJ) | Closed | Business
25934 | User Story | Filter warnings maintain screen | Nagaraj Puttakota (RAJ) | Closed | Business
63420 | User Story | Introducing details panel in warning screen | Shraddha Khare | Closed | Business
18497 | Feature | Maintain Warnings - International | Kishore | New | Business | Simple | 4 | 2017-10-10
19833 | User Story | Maintainer can logon to the maintain portal | Holger | Closed | Business
21935 | User Story | Maintainer can logout from the maintain portal | Holger | Closed | Business
26529 | User Story | Ensure that all changes being saved before leaving the screen - FSA |  | Closed | Business
26530 | User Story | Ensure that all changes being saved before leaving the screen - Cyles |  | Closed | Business
26532 | User Story | Ensure that all changes being saved before leaving the screen - Workspace settings |  | Closed | Business
26541 | User Story | Ensure that all changes being saved before leaving the screen - documents |  | Closed | Business
27338 | User Story | Ensure that all changes being saved before leaving the screen - FSA audit tests |  | Closed | Business
27339 | User Story | Ensure that all changes being saved before leaving the screen - GAA audit tests |  | Closed | Business
27340 | User Story | Ensure that all changes being saved before leaving the screen - Materiality |  | Closed | Business
27341 | User Story | Ensure that all changes being saved before leaving the screen - GAA |  | Closed | Business
27342 | User Story | Ensure that all changes being saved before leaving the screen - Risks |  | Closed | Business
27343 | User Story | Ensure that all changes being saved before leaving the screen - warnings |  | Closed | Business
59105 | User Story | Character limitations for maintaining elements | Nagaraj Puttakota (RAJ) | Closed | Business
59106 | User Story | Library Maintainer ID information is shown | Shraddha Khare | Closed | Business
59338 | User Story | Description field should allow to enter line breaks and text formatting | Shraddha Khare | Closed | Business
68184 | User Story | Customize scope auto-complete box | Stephan Matthee | Closed | Business
77699 | User Story | Character limitations for maintaining elements | Nagaraj Puttakota (RAJ) | Closed | Business
104840 | User Story | Consistent options to expand/collapse | Shraddha Khare | Closed | Business
107953 | User Story | Consistent column headers across library screens | Shraddha Khare | Resolved | Business
14721 | Feature | Condition editor | Kishore | New | Business | Medium | 7.5 | 2017-10-12
25311 | User Story | Preview changes for document maintain screen before publishing | Shraddha Khare | Closed | Business
25313 | User Story | Remove a change made to the document from the preview list | Shraddha Khare | Closed | Business
25314 | User Story | Preview changes for folder maintain screen before publishing | Shraddha Khare | Closed | Business
25316 | User Story | Remove a change made to the folders from the preview list | Shraddha Khare | Closed | Business
81573 | User Story | Remove a change made to the placeholders from the preview list | Shraddha Khare | Closed | Business
83677 | User Story | Remove a change made to the Report from the preview list | Shraddha Khare | Closed | Business
25312 | User Story | Publish documents changes to next environment | Shraddha Khare | Resolved | Business
25315 | User Story | Publish Folder changes to next environment | Shraddha Khare | Resolved | Business
14727 | Feature | Questionnaire - Maintain Sections | Laxmi | New | Business | Medium | 7.5 | 2017-10-13
22501 | User Story | Memberfirm maintainer is notified about international changes | subans | Active | Business
9223 | Feature | Maintain document manager - International | Nath Harsha | New | Business | Complex | 10 | 2017-10-15
19001 | User Story | Preview changes for FSA maintain screen before publishing | Shraddha Khare | Closed | Business
22903 | User Story | Remove a change made to the FSAs from the preview list | Shraddha Khare | Closed | Business
73641 | User Story | Remove a change made to the workspace settings from the preview list | Shraddha Khare | Closed | Business
73642 | User Story | Remove a change made to the materiality from the preview list | Shraddha Khare | Closed | Business
25025 | User Story | Publish FSA changes to next environment | Shraddha Khare | Resolved | Business
11707 | Feature | Rule editor - UX | Laxmi | New | Business | Medium | 7.5 | 2017-10-16
25308 | User Story | Preview changes for Cycle maintain screen before publishing | Nagaraj Puttakota (RAJ) | Closed | Business
25310 | User Story | Remove a change made to the Cycles from the preview list | Shraddha Khare | Closed | Business
25309 | User Story | Publish Cycle changes to next environment | Shraddha Khare | Resolved | Business
14723 | Feature | Maintain tables in questionnaires | Susmitha | New | Business | Complex | 10 | 2017-10-16
25317 | User Story | Preview changes for GAA maintain screen before publishing | Nagaraj Puttakota (RAJ) | Closed | Business
25319 | User Story | Remove a change made to the GAAs from the preview list | Shraddha Khare | Closed | Business
25318 | User Story | Publish GAAs changes to next environment | Shraddha Khare | Resolved | Business
19791 | Feature | Maintain portal | Kishore | New | Business | Complex | 10 | 2017-10-16
25326 | User Story | Preview changes for FSA audit test maintain screen before publishing | Nagaraj Puttakota (RAJ) | Closed | Business
25556 | User Story | Preview changes for GAA audit test maintain screen before publishing | Nagaraj Puttakota (RAJ) | Closed | Business
25558 | User Story | Remove a change made to the GAA audit tests from the preview list | Shraddha Khare | Closed | Business
76541 | User Story | Preview changes for review audit test maintain screen before publishing | Shraddha Khare | Closed | Business
84369 | User Story | Remove a change made to the review audit tests from the preview list | Shraddha Khare | Closed | Business
104841 | User Story | Show highlight color only for items with status Updated | Shraddha Khare | Closed | Business
25328 | User Story | Remove a change made to the audit tests from the preview list | Shraddha Khare | Ready | Business
25327 | User Story | Publish FSA audit test changes to next environment | Shraddha Khare | Resolved | Business
25557 | User Story | Publish GAA audit test changes to next environment | Shraddha Khare | Resolved | Business
76545 | User Story | Highlight modified properties in summary of changes | Nagaraj Puttakota (RAJ) | Resolved | Business
76587 | User Story | Publish Review test changes to next environment | Shraddha Khare | Resolved | Business
21895 | Feature | Maintain document manager - Publish international library | Nath Harsha | New | Business | Complex | 10 | 2017-10-16
25323 | User Story | Preview changes for risk maintain screen before publishing | Nagaraj Puttakota (RAJ) | Closed | Business
25325 | User Story | Remove a change made to the risks from the preview list | Shraddha Khare | Closed | Business
25324 | User Story | Publish Risks changes to next environment | Shraddha Khare | Resolved | Business
11405 | Feature | Maintain Tests - International | Kishore | New | Business | Complex | 10 | 2017-10-18
25329 | User Story | Preview changes for warnings maintain screen before publishing | Nagaraj Puttakota (RAJ) | Closed | Business
25331 | User Story | Remove a change made to the warnings from the preview list | Shraddha Khare | Closed | Business
25330 | User Story | Publish Warnings changes to next environment | Shraddha Khare | Resolved | Business
22801 | Feature | Maintain Financial Statement Areas (FSA) - Publish international library | Nath Harsha | New | Business | Medium | 7.5 | 2017-10-18
59211 | User Story | Render Question type - Date | samisra | Active | Business
59212 | User Story | Render Question type - Multiple choice (manual list), Checkbox | Sujeet Saraf | Active | Business
59217 | User Story | Render Question type - Number | Sujeet Saraf | Active | Business
59218 | User Story | Render Question type - Single choice, Radio | samisra | Active | Business
59220 | User Story | Render Question type - Text input | Sujeet Saraf | Active | Business
59221 | User Story | Render Question type - Dropdown | Santhosh Raju V | Active | Business
84630 | User Story | Render Question type - None | Venkat Sai Gajendrula | Active | Business
35988 | User Story | Question type - Single choice | Nagaraj Puttakota (RAJ) | Closed | Business
35989 | User Story | Question type - Multiple choice (manual list) | Nagaraj Puttakota (RAJ) | Closed | Business
35990 | User Story | Question type - table | Shraddha Khare | Closed | Business
35991 | User Story | Question type - Text input | Nagaraj Puttakota (RAJ) | Closed | Business
35992 | User Story | Question type - Number | Nagaraj Puttakota (RAJ) | Closed | Business
35993 | User Story | Question type - Dropdown | Nagaraj Puttakota (RAJ) | Closed | Business
54839 | User Story | Question type - Date | Nagaraj Puttakota (RAJ) | Closed | Business
60140 | User Story | Preview and Publish Question type - None, Date, Number, Text input | Shraddha Khare | Closed | Business
60141 | User Story | Preview and Publish Question type - Multiple choice (manual list) | Shraddha Khare | Closed | Business
60143 | User Story | Preview and publish question field type - Dropdown based on engagement data | Shraddha Khare | Closed | Business
60145 | User Story | Preview and Publish Question type - Single choice | Shraddha Khare | Closed | Business
60146 | User Story | Preview and publish changes made to a Question type - Dropdown | Shraddha Khare | Closed | Business
78879 | User Story | Question type - None | Nagaraj Puttakota (RAJ) | Closed | Business
22827 | Feature | Maintain Tests - Publish international library | Gurudas | New | Business | Medium | 7.5 | 2017-10-18
60849 | User Story | Render help text block in questionnaire preview | Santhosh Raju V | Active | Business
36589 | User Story | View help text in questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
36593 | User Story | Add a new text block to a questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
36594 | User Story | Move a help text in a questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
36595 | User Story | Delete a help text from a questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
59149 | User Story | Update an existing text block in a questionnaire | Nagaraj Puttakota (RAJ) | Closed | Business
59227 | User Story | Provide conditional formatting for a text block | Nagaraj Puttakota (RAJ) | Closed | Business
60844 | User Story | Preview and publish changes made to a text block in a questionnaire | Shraddha Khare | Closed | Business
93805 | User Story | Changes in Section, Text block, Question Title and number of characters in the title | Shraddha Khare | Closed | Business
22853 | Feature | Maintain Risks - Publish international library | Gurudas | New | Business | Medium | 7.5 | 2017-10-19
53065 | User Story | Define and develop a storage solution for questionnaire maintenance in AMT | Sree Adigopula | Closed | Architectural
117178 | User Story | Render Engine and Rule Engine Technical component | sumadh | Ready | Architectural
3343 | Feature | Enable/disable features based on Initial Scoping Questions | Kishore | New | Architectural | Complex | 10 | 10/19/2017
56570 | User Story | Validate questionnaire - duplicate question ID | Shraddha Khare | Closed | Business
56209 | User Story | Question, section or text block scope conflicts with document properties | Shraddha Khare | Ready | Business
56465 | User Story | Question, section or text block scope conflicts with parent section scope | Shraddha Khare | Ready | Business
9224 | Feature | Add new answers to Initial Scoping questions | harsha | New | Business | Complex | 10 | 10/19/2017
58005 | User Story | Enable single sign-off | Nagaraj Puttakota (RAJ) | Closed | Business
58006 | User Story | Disable single sign-off | Nagaraj Puttakota (RAJ) | Closed | Business
53064 | Feature | Technology / infrastructure needed for questionnaires | Susmitha | New | Architectural | Medium | 7.5 | 10/19/2017
59230 | User Story | Add a new tickmark to the library | Nagaraj Puttakota (RAJ) | Closed | Business
59231 | User Story | Update tickmarks in the library | Nagaraj Puttakota (RAJ) | Closed | Business
59232 | User Story | Delete a tickmark from the library | Nagaraj Puttakota (RAJ) | Closed | Business
59233 | User Story | Update sort order of tickmarks | Nagaraj Puttakota (RAJ) | Closed | Business
59344 | User Story | Preview changes for tickmarks maintain screen before publishing | Nagaraj Puttakota (RAJ) | Closed | Business
73934 | User Story | Remove a change made to the tickmarks from the preview list | Shraddha Khare | Closed | Business
71618 | User Story | API Integration for tickmarks | Nagaraj Puttakota (RAJ) | Resolved | Business
73933 | User Story | Publish Tickmarks changes to next environment | Shraddha Khare | Resolved | Business
21897 | Feature | Maintain document manager - Memberfirm related |  | New | Business | Simple | 4 | Future Features
59360 | User Story | Add and Update a new leadsheet code to the library | Nagaraj Puttakota (RAJ) | Closed | Business
59366 | User Story | Delete L/S code from the library | Nagaraj Puttakota (RAJ) | Closed | Business
60458 | User Story | Update sort order of L/S code in the library(reordering) | Stephan Matthee | Closed | Business
61120 | User Story | Filter L/S code maintain screen | Stephan Matthee | Closed | Business
63417 | User Story | Introducing details panel in L/S screen | Shraddha Khare | Closed | Business
73935 | User Story | Preview changes for L/S codes maintain screen before publishing | Nagaraj Puttakota (RAJ) | Closed | Business
73936 | User Story | Remove a change made to the L/S codes from the preview list | Shraddha Khare | Closed | Business
60942 | User Story | Publish L/S codes changes to next environment | Shraddha Khare | Resolved | Business
71619 | User Story | API integration for leadsheets | Nagaraj Puttakota (RAJ) | Resolved | Business
305.5

## Features to be covered
Functional Features |  |  |  |  | Architectural Features
ID | Work Item Type | Title | State | Status | ID | Work Item Type | Title | State
11403 | Feature | Maintain Financial Statement Areas (FSA) - International | Active |  | 14870 | Feature | Data Model Implementation | Active
25485 | Feature | Validate library | Active |  | 25770 | Feature | Technical design for Engagement Reporting | Active
3352 | Feature | Publish libraries | New |  | 3343 | Feature | Enable/disable features based on Initial Scoping Questions | New
9223 | Feature | Maintain document manager - International | New |  | 11886 | Feature | Localization | New
9224 | Feature | Add new answers to Initial Scoping questions | New |  | 12041 | Feature | UX Standardization | New
9835 | Feature | Maintain WorkspaceSettings | New |  | 12043 | Feature | Application server configuration settings | New
11404 | Feature | Maintain General Audit Areas (GAA) - International | New |  | 13176 | Feature | Technical Designs for Library | New
11405 | Feature | Maintain Tests - International | New |  | 14880 | Feature | Library API Services | New
11406 | Feature | Maintain Risks - International | New |  | 53064 | Feature | Technology / infrastructure needed for questionnaires | New
11407 | Feature | Maintain Cycles - International | New
11408 | Feature | Maintain Materiality | New |  |  |  | Total: | 9
11706 | Feature | Rules for document manager | New
11707 | Feature | Rule editor - UX | New
11766 | Feature | Rules for audit tests | New
14721 | Feature | Condition editor | New
14723 | Feature | Maintain tables in questionnaires | New
14726 | Feature | Questionnaire - Maintain Document | New
14727 | Feature | Questionnaire - Maintain Sections | New
14728 | Feature | Questionnaire - Maintain Questions | New
14736 | Feature | Rules for risks | New
14743 | Feature | Rules for FSA/GAA | New
14744 | Feature | Rules for cycle | New
14751 | Feature | Rules for warnings | New
18497 | Feature | Maintain Warnings - International | New
19791 | Feature | Maintain portal | New
21895 | Feature | Maintain document manager - Publish international library | New
21897 | Feature | Maintain document manager - Memberfirm related | New
22801 | Feature | Maintain Financial Statement Areas (FSA) - Publish international library | New
22804 | Feature | Maintain Cycles - Publish international library | New
22825 | Feature | Maintain General Audit Areas (GAA) - Publish international library | New
22827 | Feature | Maintain Tests - Publish international library | New
22853 | Feature | Maintain Risks - Publish international library | New
22859 | Feature | Maintain Warnings - Publish international library | New
35983 | Feature | Questionnaire - Question types | New
36580 | Feature | Questionnaires - Maintain Text block (help, instructions, warning) | New
56155 | Feature | Validate questionnaires | New
57986 | Feature | Other rules | New
59229 | Feature | Maintain Tickmarks | New
59346 | Feature | Maintain Leadsheet codes | New
|  | Total: | 39

## Features to be grouped
Grouped Features:
|  | Maintain Screens Feature |  |  |  | Publish Feature
11403 | Feature | Maintain Financial Statement Areas (FSA) - International | Active | 3352 | Feature | Publish libraries | New
9223 | Feature | Maintain document manager - International | New | 21895 | Feature | Maintain document manager - Publish international library | New
9835 | Feature | Maintain WorkspaceSettings | New | 22801 | Feature | Maintain Financial Statement Areas (FSA) - Publish international library | New
11404 | Feature | Maintain General Audit Areas (GAA) - International | New | 22804 | Feature | Maintain Cycles - Publish international library | New
11405 | Feature | Maintain Tests - International | New | 22825 | Feature | Maintain General Audit Areas (GAA) - Publish international library | New
11406 | Feature | Maintain Risks - International | New | 22827 | Feature | Maintain Tests - Publish international library | New
11407 | Feature | Maintain Cycles - International | New | 22853 | Feature | Maintain Risks - Publish international library | New
11408 | Feature | Maintain Materiality | New | 22859 | Feature | Maintain Warnings - Publish international library | New
14723 | Feature | Maintain tables in questionnaires | New
18497 | Feature | Maintain Warnings - International | New |  |  | Rules Feature
19791 | Feature | Maintain portal | New | 11706 | Feature | Rules for document manager | New
21897 | Feature | Maintain document manager - Memberfirm related | New | 11707 | Feature | Rule editor - UX | New
36580 | Feature | Questionnaires - Maintain Text block (help, instructions, warning) | New | 11766 | Feature | Rules for audit tests | New
59229 | Feature | Maintain Tickmarks | New | 14736 | Feature | Rules for risks | New
59346 | Feature | Maintain Leadsheet codes | New | 14743 | Feature | Rules for FSA/GAA | New
14726 | Feature | Questionnaire - Maintain Document | New | 14744 | Feature | Rules for cycle | New
14727 | Feature | Questionnaire - Maintain Sections | New | 14751 | Feature | Rules for warnings | New
14728 | Feature | Questionnaire - Maintain Questions | New | 57986 | Feature | Other rules | New
|  | Individual Features |  |  |  | Validate Feature
9224 | Feature | Add new answers to Initial Scoping questions | New | 25485 | Feature | Validate library | Active
14721 | Feature | Condition editor | New | 56155 | Feature | Validate questionnaires | New
35983 | Feature | Questionnaire - Question types | New

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy hh:mm AM/PM | readOnlyTestRange_General | readOnlyTestRange_M/d/yyyy h:mm AM/PM